## Sheet1
www.goodoldmanoj.com
Project | Task | Start | Day 4 | Day 3 | Day 2 | Day 1
Pencarian Bahan Materi Google Glass | Mencari Bahan Apa itu Google Glass | 4 | 0 | 0 | 0 | 3
| Mencari Bahan Kelebihan dan Kekurangan Google Glass | 4 | 0 | 0 | 0 | 5
| Mencari Bahan Cara Kerja Google Glass | 4 | 0 | 0 | 0 | 2
Pengenalan Google Glass | Apa itu Google Glass? | 3 | 0 | 0 | 4 | 0
| Kelebihan dan Kekurangan Google Glass | 3 | 0 | 0 | 2 | 0
| Cara Kerja Google Glass | 3 | 0 | 0 | 3 | 0
Bagian - Bagian Google Glass | Aplikasi Google Glass | 4 | 1 | 5 | 0 | 0
| Fitur Google Glass | 5 | 2 | 4 | 0 | 0
| Hardware Google Glass | 4 | 1 | 2 | 0 | 0
Detil Google Glass | Perbedaan Google Glass dengan Gadget Lainnya | 4 | 0 | 0 | 0 | 3
| Spesifikasi Google Glass | 5 | 0 | 0 | 0 | 2
| SMS Iphone Hadir di Google Glass | 6 | 0 | 0 | 0 | 7
Google Glass | Bahaya Google Glass | 2 | 0 | 0 | 1 | 0
| Kapan Google Glass akan Diliris? | 3 | 0 | 0 | 4 | 0
| Hasil Foto Google Glass | 4 | 0 | 0 | 3 | 0
Biodata | Biodata Andi | 5 | 0 | 4 | 0 | 0
| Biodata Edward | 5 | 0 | 4 | 0 | 0
| Biodata Andy Syahputra | 5 | 0 | 4 | 0 | 0
Google Glass Detail | Gambar Bagian - Bagian Google Glass | 4 | 3 | 0 | 0 | 0
| Harga Google Glass | 3 | 3 | 0 | 0 | 0
| Fungsi Google Glass | 2 | 1 | 0 | 0 | 0
Biografi | Biografi Andi | 1 | 0 | 0 | 0 | 1
| Biografi Edward | 1 | 0 | 0 | 0 | 1
| Biografi Andy Syahputra | 1 | 0 | 0 | 0 | 1
Campuran | Biografi Lary Page | 2 | 0 | 0 | 1 | 0
| Dasar Perintah Google Glass | 2 | 0 | 0 | 1 | 0
| GC berbahaya bagi anak - anak | 2 | 0 | 0 | 1 | 0
Campuran | Biografi Lary Page | 3 | 0 | 2 | 0 | 0
| Dasar Perintah Google Glass | 6 | 0 | 4 | 0 | 0
| GC berbahaya bagi anak - anak | 2 | 0 | 1 | 0 | 0
Biodata Tokoh Dunia Teknologi | Biodata Bill Gates | 3 | 2 | 0 | 0 | 0
| Biodata Mark Zuckerberg | 3 | 2 | 0 | 0 | 0
| Biodata Jack Dorsey | 4 | 3 | 0 | 0 | 0
Biografi Tokoh Dunia Teknologi | Biografi Bill Gates | 5 | 0 | 0 | 0 | 4
| Biografi Mark Zuckerberg | 5 | 0 | 0 | 0 | 3
| Biografi Jack Dorsey | 5 | 0 | 0 | 0 | 4
Teknologi | Biografi Jonathan Abrams | 5 | 1 | 1 | 2 | 0
| Siapa Penemu Komputer Pertama di dunia | 5 | 1 | 1 | 3 | 0
| Teknologi terbaru di dunia | 5 | 1 | 1 | 4 | 0
Ideal - Remaining efforts in uninterrupted working hours |  | 142 | 106.5 | 71 | 35.5 | 0
Actual - Remaining efforts in uninterrupted working hours |  | 142 | 21 | 33 | 29 | 36
Note on F5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on G5: Remaining effort as of that day to complete the task.It's NOT last day effort - hours worked. So this can go up if new challenges got uncovered